## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 45 (Team Number)
PROJECT NAME | Micro-Content Powered Transit M-Commerce
PROJECT MENTOR (sponsor) | Digital Augumentum - Mr. Ramachandran
TEAM MEMBERS | Naga Sai Ritvik Modumudi
Keshava Kishora Nanda Veerapuneni
Venishetty Hari Chandana
Paridhi Jain
Navdha Bansal

## Status
PROJECT NUMBER | 45 (Team Number)
PROJECT NAME | Micro-Content Powered Transit M-Commerce
PROJECT MENTOR (sponsor) | Digital Augumentum - Mr. Ramachandran
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 15 - January 22)
Project synopsis writeup | Preparation | Navdha Bansal | 0.5 | 1 | Done |  | -0.5 | 50
Identifying Questions we have in the synopsis | Requirements | Keshav | 1 | 1 | Done |  | 0 | 0
Categorizing Questions | Documentation | Ritvik | 1 | 2 | Done |  | -1 | 50
GIT Repository setup | Preparation | Navdha Bansal | 0.33 | 0.25 | Done |  | 0.08 | 32
Client meeting | Coordination | Hari Chandana | 0.5 | 0.66 | Done |  | -0.16 | 24.2424
Team Meeting | Coordination | Paridhi Jain | 0.5 | 0.33 | Done | Divided ourselves into frontend and backend teams. | 0.17 | 51.5152
Readup on Firebase | Preparation | Hari Chandana | 2 | 2.5 | Done |  | -0.5 | 20
Setup Firebase Account | Preparation | Hari Chandana | 1 | 0.5 | Done |  | 0.5 | 100
Test Firebase Features | Preparation | Ritvik | 2 | 2 | Done |  | 0 | 0
Week 2 (January 22 - January 29)
Install Android Studio | Preparation | Paridhi Jain | 1.5 | 2.5 | Done |  | -1 | 40
Learn basic Android Studio | Preparation | Keshav | 4.5 | 3 | Done |  | 1.5 | 50
Team Meeting | Coordination | Navdha Bansal | 0.5 | 0.33 | Done |  | 0.17 | 51.5152
Presentation for Client Meet | Preparation | Keshav | 0.5 | 0.5 | Done
Status tracker | Documentation | Ritvik | 0.5 | 0.5 | Done |  | 0 | 0
Learn basic App Development | Preparation | Navdha Bansal | 7.5 | 8 | Done
Create Basic App | Development | Paridhi Jain | 2.5 | 3 | Done
Create basic Schemas | Development | Hari Chandana | 2.5 | 2 | Done
Week 3 (January 29 - February 5)
SRS Doc | Documentation | Keshav | 3 | 3 | Done
ProjectPlan Doc | Documentation | Hari Chandana | 2 | 1 | Done
Firestore Testing | Preparation | Hari Chandana | 1.5 | 1 | Done |  | 0.5 | 50
Firebase Functions Testing | Preparation | Ritvik | 2 | 1.5 | Done
UI communication with Firebase | Development | Navdha Bansal | 2 | 2 | Done
Client meeting | Coordination | Paridhi Jain | 1 | 0.5 | Done
Week 4 (February 5 – February 12)
Making Page Scrollable (Figma) | Development | Keshav | 2 | 2 | Done |  | 0 | 0
Populating Database | Development | Paridhi Jain | 0.5 | 0.5 | Done
Adding more features to UI | Design | Ritvik | 2 | 3 | Done
Team Meeting | Coordination | Hari Chandana | 0.5 | 0.33 | Done |  | 0.17 | 51.5152
Client meeting | Coordination | Navdha Bansal | 0.5 | 0.5 | Done
Week 5 (February 12 – February 19)
UI improvements | Design | Keshav | 4 |  | Ongoing
Learn how to package app for deployment | Preparation | Ritvik | 2 | 1.5 | Done
Deploying to PlayStore | Delivery | Navdha, Paridhi | 6 | 5 | Done |  | 1 | 20
Populating Database through script | Development | Ritvik, Hari Chandana | 3 | 2.5 | Done
SRS Doc | Documentation | All | 3 | 3 | Done
Status Tracker | Documentation | Hari Chandana | 0.5 | 0.5 | Done |  | 0 | 0
Client meeting | Coordination | Keshav | 0.5 | 0.5 | Done
Week 6 (February 19 – February 26)
Making Home Page | Design | Keshav | 4 | 5 | Done |  | -1 | 20
UI Improvements for LearnPerk Page | Design | Navdha, Paridhi | 4 |  | Ongoing
Search API | Development | Ritvik, Hari Chandana | 3 |  | Ongoing
Make videos playable | Development | Keshav | 3.5 | 3 | Done |  | 0.5 | 16.6667
Test Plan Tracker | Documentation | Hari Chandana, Paridhi, Navdha | 4 | 4 | Done
Client meeting | Coordination | Ritvik | 0.5 | 0.5 | Done
Week 7 (February 26 - March 4)
Integrating app with IRCTC Home page | Development | Keshav, Navdha, Ritvik | 6 | 5.5 | Done
Team Meeting | Coordination | Paridhi | 0.5 | 0.5 | Done |  | 0 | 0
Client meeting | Coordination | Hari Chandana | 0.5 | 0.5 | Done |  | 0 | 0
Week 8 (March 4 – March 11)
Dummy E-Commerce App | Development | Navdha,Paridhi,Hari Chandana | 4 | 3 | Done |  | 1 | 33.3333
Implementing Coin system | Development | Ritvik | 5 | 4 | Done |  | 1 | 25
Making IRCTC Home page | Design | Keshav | 6 | 5.5 | Done |  | 0.5 | 9.0909
Design Document | Documentation | All | 5 | 5 | Done |  | 0 | 0
Team Meeting | Coordination | Paridhi | 0.5 | 0.5 | Done |  | 0 | 0
Client meeting | Coordination | Navdha | 0.5 | 0.5 | Done |  | 0 | 0
Week 9 (March 11 – March 18)
Implementing Video player in new screen | Development | Keshav, Ritvik | 4 |  | Planned
Preparation for R1 | Preparation | All | 7.5 |  | Planned
Improvements for E-Commerce page | Development | Navdha, Paridhi | 3 |  | Planned
Team Meeting | Coordination | Hari Chandana | 0.5 |  | Planned
Client meeting | Coordination | Hari Chandana | 0.5 |  | Planned